## Sheet1
Date | Issue | Domain | Status
8th July 2023 | Apply changes to cell when slected AL is clicked | Frontend | Fixed
8th July 2023 | Only font but not color applied to selected AL cells issue. | Frontend | Fixed
8th July 2023 | Let selected cells for both tenure and AL days be empty upon month shift | Frontend | Fixed
8th July 2023 | Add cell hover over feature | Frontend | Ongoing
8th July 2023 | Organize files.Maybe structurally frontend backend | Frontend | Fixed
9th July 2023 | Study javaScript obfuscation and minification | Frontend | Fixed
10th July 2023 | Study Login Features | BackEnd | Fixed
12th July 2023 | Study Async function | BackEnd | Fixed
13th July 2023 | Fix EmployeeCreator.js.The async function doenst looks right. | BackEnd | Fixed
23rd July 2023 | Add ajax feature to login page.Login page stay put if discrepants login. | BackEnd | Fixed
23rd July 2023 | Checking against database for login | BackEnd | Fixed
30th July 2023 | Passing argument to html upon succesful login | BackEnd | Fixed
31stJuly2023 | Vulnerabilites issue og bypassing login | BackEnd | Ongoing
Note on D2: herng: Defining colorSelectedALCells() and loading it fixed the issue
Note on D3: herng: Fixed.Removed inline CSS and have ebrything defined by CSS class list. with this approach,the calendar need not be loaded each time to reflect the changes.
Note on D6: herng: Look out for the relative path traversing.When requesting for a php file,the relative to it is the localhost/server hierachy which is likely the HTML location.
Note on D10: herng: Is working fine all this while.Async await is the best approach for cleaner codes.Promises approach will require more files/codes for instatiazion.
Note on D12: herng: herng: Make sure the event btween AJAX and PHP dont get jumble up.Let PHP do the authentication and pass the result to AJAX only.Let Ajax do the redirect.
Note on D13: herng: Fixed and worked.However this pose a threat as the redirect page can be accessed bypassing login page..Below item to check on this
Note on D14: threat of the redirect page can be accessed bypassing login page